|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
| **Town of Keenesburg 2016 Street Maintenance & Repair Project Schedule** |
|   |   |   |   |
| **ACTIVITY** | **STREET (FROM- TO)** | **DURATION** | **DATES** |
| **CONCRETE REPAIR** |  | 5 days | 4/18/16 thru 4/22/16 |
| **PATCHING** | Dickson, Kipp & Broadway | 4 days  | 4/18/16 thru 4/21/16 |
| **MILLING**  | OWEN, (CEDAR - MAIN) | 1 day | 4/19/2016 |
| **MILLING** | PINE, (OWEN - CRAWFORD) | 1 day | 4/19/2016 |
| **MILLING** | -N. 1ST., (MARKET - MAIN) | 1 day | 4/19/2016 |
| **BASKETBALL COURT PREP** | N/A | 1 day | 4/21/2016 |
| **SUBGRADE PREP**  | Owen, (Cedar - Main) | 9 days | 4/19/2016 thru 4/29/2016 |
| **PAVING**  | North 1st, (Market - Main) | 1 day | 4/20/2016 |
| **PAVING**  | Pine, (Owen - Crawford) | 1 day | 4/21/2016 |
| **PAVING** | Owen-bottom lift, (Pine-Main) | 1 day | 4/22/2016 |
| **PAVING**  | Owen, (Cedar - Main) | 1 day | 4/28/2016 |
| **CRACKSEAL** | Dickson, Kipp & Broadway | 2 days  | 4/25/2016 thru 4/26/2016 |
| **RESURFACE BASKETBALL COURT** | Owen (Cedar-Pine) | 1 day | 4/25/2016 |
| **WATERLINE REPLACEMENT** | Owen (Cedar-Pine) | 5 days | 4/25/2016 thru 4/29/2016 |
| **MILLING FOR WATERLINE** | Miller, (Kipp - Woodward) | 1 day | 5/2/2016 |
| **WATERLINE REPLACEMENT** | Miller St. (Kipp-Woodward) | 5 days | 5/02/2016 thru 5/06/2016 |
| **MILLING**  | Nelson St., (Cedar - Elm) | 1 day | 5/2/2016 |
| **MILLING** | Crawford, (Pine-Elm) | 1 day | 5/2/2016 |
| **SUBGRADE PREP** | Nelson, (Cedar - Elm) | 4 days  | 5/02/2016 thru 5/05/2016 |
| **SUBGRADE PREP**  | Crawford, (Pine - Elm) | 2 days  | 5/04/2016 & 5/05/2016 |
| **PAVING**  | Nelson St., (Cedar - Elm) | 1 day | 5/6/2016 |
| **PAVING** | Crawford, (Pine-Elm) | 1 day | 5/6/2016 |
| **MILLING**  | Kipp (Miller - Midblock) | 1 day | 5/10/2016 |
| **MILLING**  | Main St, (CR398- Broadway) | 1 day | 5/10/2016 |
| **MILLING**  | Gandy, (Pine - Elm) | 1 day | 5/10/2016 |
| **MILLING**  | Miller St. (Kipp-Woodward) | 1 day | 5/10/2016 |
| **MILLING**  | Stewart, (Kipp-Woodward) | 1 day | 5/10/2016 |
| **SUBGRADE PREP** | Miller, Waterline cut & Gandy | 1/2 day | 5/9/2016 |
| **SUBGRADE PREP** | Gandy, (Pine - Elm) | 1-1/2 day  | 5/09/2016 & 5/10/2016 |
| **PAVING** | Miller St. (Kipp-Woodward)-patch | 1 day | 5/9/2016 |
| **PAVING** | Miller St., (Kipp-Woodward) | 1 day | 5/10/2016 |
| **PAVING** | Gandy, (Pine - Elm) | 1 day | 5/11/2016 |
| **SUBGRADE PREP** | Main St, (CR398- Broadway) | 2 days  | 5/11/2016 & 5/12/2016 |
| **PAVING** | Main St, (CR398- Broadway) | 1 day | 5/13/2016 |
| **WATERLINE REPLACEMENT** | Kipp (Miller - Midblock) | 5 days | 5/09/2016 thru 5/13/2016 |
| **SUBGRADE PREP** | Kipp (Miller - Midblock) | 2 days  | 5/16/2016 & 5/17/2016 |
| **PAVING** | Kipp (Miller - Midblock) | 1 day | 5/18/2016 |
| **WATERLINE REPLACEMENT,**  | Stewart, (Kipp-Woodward) | 5 days | 5/16/2016 thru 5/20/2016 |
| **MILLING**  | Broadway, (Market - Main) | 1 day | 5/25/2016 |
| **MILLING**  | Elm, (Shepard - Woodward) | 1 day | 5/25/2016 |
| **PAVING** | Stewart, (Kipp-Woodward) | 1 day | 5/23/2016 |
| **PAVING** | Broadway, (Market - Main) | 1 day | 5/24/2016 |
| **PAVING** | Elm, (Shepard - Woodward) | 2 days  | 5/25/2016 & 5/26/2016 |
| **CHIPSEALING** | Dickson, Kipp, Stewart & Broadway | 2 days  | 7/11/2016 & 7/12/2016 |
|  |  |  |  |
| **\*\*\*ANTICIPATED CONCRETE REPAIR SEQUENCE:\*\*\*** |  |  |
| 1-Pine S |  |  |  |
| 2-Owens st. |  |  |  |
| 3-Half crosspan and C & G work at Elm & Gandy |  |  |
| 4-Elm St |  |  |  |
| 5-Broadway |  |  |  |
| 6- Remaing half of crosspan and C & G work at Elm & Gandy |  |  |
| 7-Concrete work related to irrigation pipe replacement. |  |  |
|  |  |  |  |